## Sheet1
FINDING NUMBER | OPEN OR CLOSED | FINDING NAME | DESCRIPTION | TYPE OF FINDING | CATEGORY | TARGET COMPLETION DATE | DATE COMPLETED | COMPLETED BY | INTERNAL AUDITOR VALIDATION DATE | RECORD OF EFFORT | COMMENTS
2013-001 | OPEN | BANK RECONCILIATIONS | Timeliness and review process (repeated and updated) | Material Weakness | Cash & Investments | 2017-12-01 |  |  |  | August 2017 - Deposits posed a bit of difficulty. This will be resolved very shortly. NNMC will now number deposits utilizing pre-printed, numbered deposit slips. The deposit slip numbers will be recorded by the bank (just like check numbers). Once this is implemented, the bank reconciliation process will be considered automated and will be executed more efficiently and effectively. July 2017 - Automated reconciliation of checks has already been sucessfully tested and is ready for mplementation. Procedures have been written. The IT Director is in the process of establishing a method to automate the reconciliation of deposits. June 2017 - A task force has been established in order to implement the cash reconciliation functionality within the ERP System (Banner). The task force is comprised of accounting and IT Staff and we ancipate meeting bi-weekly. May 2017 -- Looking at Banner Modules to incorporate accounting software to replace database processes
2013-002 | OPEN | BANK RECONCILIATIONS | Timeliness and review process - Foundation (repeated and updated) | Material Weakness | Cash & Investments | 2017-12-01 |  |  |  | July 2017 - Automated reconciliation of checks has already been sucessfully tested and is ready for mplementation. Procedures have been written. The IT Director is in the process of establishing a method to automate the reconciliation of deposits. June 2017 - A task force has been established in order to implement the cash reconciliation functionality within the ERP System (Banner). The task force is comprised of accounting and IT Staff and we ancipate meeting bi-weekly. May 2017 -- Looking at Banner Modules to incorporate accounting software to replace database processes
2013-003 | OPEN | CAPITAL ASSETS | Physical Inventory Certification & Safeguarding (repeated and updated) | Significant Deficiency | Capital Assets | 2018-06-01 |  |  |  | June 2017 -The College Accounting & IT staff are currently in the process of conducting an inventory of the capital assets summary of which will be submitted to the Board of Directors for review and certification. May 2017 -- Assessing physical asset inventory
2013-007 | OPEN | DISASTER RECOVERY PLAN AND PASSWORD POLICIES | Repeated and updated | Significant Deficiency | Information Technology | 2017-08-11 |  |  |  | August 2017 - Mandatory safety and security training was conducted during convocation week (August 7 through 11). The majority of staff attended; however, there were some staff members responsible for customer service that could not attend. We will reschedule a training for those that we missed by year-end. June 2017 - The College is in the process of revising the Campus Emergency Response Plan (CERP). It is anticiapted to be completed no later than December 2017. The College implemented a new password policy May 2017 -- Campus Emergency Response Team (CERT) has been tasked with including this issue in the Campus Emergency Response Plan (CERP) and briefed to all faculty and staff during Convocation Week activities in August.
2015-001 | OPEN | TRAVEL AND PER DIEM | Repeated and updates | Other Noncompliance | Travel and Per Diem |  |  |  |  | No change for August 2017. June 2017 - The checklist is currently under evaluation in order to ensure that process are being followed and that there are no issues. The evaluation will be completed no later than September 30, 2017.
2016-001 | OPEN | LATE AUDIT REPORT |  | Material Non-Compliance | Late Audits | 2017-11-01 |  |  |  | August 2017 - An RFP for a new audit firm was issued and advertised. Four bids were received. All four audit firms are aware of the timeline and all four indicated they would attempt to meet State Auditor deadlines; however, in light of the past audit results, there may be delay. July 2017 - NNMC's contract with JAG has been terminated. An RFP is currently in progress. This may affect the timliness of the audit; however, after discussions with the State Auditor's Office, this is believed to be the best course of action. June 2017 -- The College President and the FY18 annual auditing firm (Jaramillo Accounting Group) have already discussed strategies for starting the FY18 audit as early as July or August, in order to meet the November 1 deadline. May 2017 -- The College President and the FY18 annual auditing firm (Jaramillo Accounting Group) have already discussed strategies for starting the FY18 audit as early as July or August, in order to meet the November 1 deadline. The only obstacle at present is the timing of the forensic audit (please see the comments for 2016-002 above), but the college will be aggressive at making sure we lean forward in every way possible.
2016-002 | OPEN | POTENTIAL FRAUD, FORGERY, EMBEZZLEMENT, LARCENY AND NON-COMPLIANCE |  | Material Weakness | State Law Compliance - Other | 2017-11-01 |  |  |  | August 2017 - A forensic audit firm was hired (McHard Accounting & Consulting). The firm began by specifically targeting federal funding, and more specifically, the Title III Grant because draws are currently being held back. Preliminarily, the forensic accountants have verified support for Title III expenditures and were pleased with the results. However, they did not test expenditures for the three partner schools due to the fact that those records are held at those schools. July 2017 - Discussions have been held with the State Police investigator. The investigator has completed his work and documents and the former Finance Director's office have been released. The President has attempted repeatedly to make contact with the DA and awaits a return call. June 2017 -- In late April 2017, the College President and VP had a meeting with the District Attorney handling the case, as well as the NM State Police. The College was given the authority to order a forensic audit to assist with the investigation. We will be communicating with the DA and State Police to determine the next step forward. May 2017 -- In late April 2017, the College President and VP had a meeting with the District Attorney handling the case, as well as the NM State Police. The College has now been given the authority to order a forensic audit to assist with the investigation. We are in the process of filling out a Request for Proposal (RFP) and hope to have the forensic audit completed before completion of the FY18 Annual Audit in November 2017.
2016-003 | OPEN | INSUFFICIENT ATTENTION AND ACCOUNTABILITY OVER ACCOUNTING AND INTERNAL CONTROLS |  | Material Weakness | Financial Reporting | 2017-08-01 |  |  |  | August 2017 - the forensic accountants have been asked to review controls implemented thus far and make recommendations. They began their work last Tuesday, August 8 and hope to have a completed report to NNMC by the end August. July 2017 - The Interim VP for Finance & Admin continues to assess the internal control system in order to implement the necessary changes. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-004 | OPEN | INSUFFICIENT SECURITY OF ACCOUNTING RECORDS/BACKUP OF ELECTRONIC DOCUMENTS |  | Material Weakness | State Law Compliance - Other | 2017-08-01 |  |  |  | August 2017 - Still in process. No change in status. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-005 | OPEN | PROCUREMENT CODE VIOLATIONS |  | Material Weakness | Procurement | 2017-11-01 |  |  |  | August 2017 - Still in process.June 2017 - The new VP of Finance & Administration has initiated contact with the State Pruchasing Agent in order to establish a long-term plan for the College that encopasses procurement code training and certification for all College employees involved in the procurement process. May 2017 -- The College's procurement officer is scheduled for specialized training May 15-16, 2017.
2016-006 | OPEN | SEGREGATION OF DUTIES |  | Material Weakness | Segregation of Duties | 2017-08-01 |  |  |  | August 2017 - Progress continues as new procedures continue to be implemented. June 2017 -- In February 2017, the College hired a new Human Resources Director. The segregation of duties will be spelled out to prevent future findings in this area. May 2017 -- In February 2017, the College hired a new Human Resources Director. The incoming Interim VP of Admin and Finance (scheduled to start June 1, 2017) will lead the search for the College's new Finance Director. The segregation of duties will be spelled out to prevent future findings in this area.
2016-007 | OPEN | FINANCIAL CLOSE AND REPORTING |  | Material Weakness | Financial Reporting | 2017-11-01 |  |  |  | August 2017 - The Students Accounts Receivable position has been filled with Ms. Jessica Holguin who was responsible for filling in while the position was vacant. This month she has been mired in work as students have returned to College. Jessica and the rest of the business staff will continue to work toward resolution of this finding. June 2017 - A review is currently under way to determine responsibility at the account level. The College is in the process of hiring a Student Accounts Receivable person. Accounting is coordinating with Financial Aid to utilize their knowledge and assistance. May 2017 - In Progress
2016-008 | OPEN | LACK OF INTERNAL CONTROLS OVER CASH RECEPTS PROCESS |  | Material Weakness | Cash and Investments | 2017-11-01 |  |  |  | August 2017 - We continue to work toward resolution of this finding and segregation has begun as we review the process. The process has been documented complete with flow charts, etc. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-009 | OPEN | LACK OF INTERNAL CONTROLS OVER CASH DISBURSEMENTS AND TRANSFER PROCESS |  | Material Weakness | Expenditures and Expenses - Other | 2017-11-01 |  |  |  | June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-010 | OPEN | LACK OF INTERNAL CONROLS OVER JOURNAL ENTRIES |  | Material Weakness | Lack of Policies, Procedures, and Internal Control Structure and Environment | 2017-11-01 |  |  |  | August 2017 - the Interim VP for Fin & Admin now reviews all JEs and posts them to the system. The new procedures are in the process of review by the Forensic Auditors. June 2017 - The new VP of Finance & Administration has initiated contact with the State Pruchasing Agent in order to establish a long-term plan for the College that encopasses procurement code training and certification for all College employees involved in the procurement process. May 2017 - In Progress
2016-011 | OPEN | NEW MEXICO STATE CONSTITUTION VIOLATION - BOARD MEMBER VACANCY |  | Non-Compliance | State Law Compliance - Other | Unknown |  |  |  | August 2017 - No change in status. June 2017 -- The College President and the President of the Board of Regents have both engaged on multiple occasions with the Governor's office on this issue. The President of the Board was confirmed for another 6 year term in March 2017. The student regent position was nominated by the governor but did not have a confirmation hearing during the legislative session. A fifth open regent position remains unfilled. May 2017 -- The College President and the President of the Board of Regents have both engaged on multiple occasions with the Governor's office on this issue. The President of the Board was confirmed for another 6 year term in March 2017. The student regent position was nominated by the governor but did not have a confirmation hearing during the legislative session. A fifth open regent position remains unfilled.
2016-012 | OPEN | TRANSFERS, DISPOSALS, AND TRACKING OF INVENTORY ITEMS LESS THAN $5,000 |  | Material Weakness | Inventory | 2017-11-01 |  |  |  | August 2017 - Still in process. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-013 | OPEN | PUBLIC MONEY ACTION VIOLATION - DEPOSITS NOT MADE WITHIN 24 HOURS |  | Non-Compliance | State Law Compliance - Public Money Act | 2017-11-01 |  |  |  | August 2017 - Processes have been documented and staff is ensuring that deposits are made within the next business day. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-014 | OPEN | NON-COMPLIANCE WITH AND INADEQUATE CONTROLS OVER THE GOVERNMENTAL CONDUCT ACT |  | Non-Compliance | Lack of Policies, Procedures or Internal Controls | 2017-09-01 |  |  |  | August 2017 - Training pertaining to the proposed code of conduct as well as the Governmental Conduct act was held the afternoon of Tuesday, August 8, 2017 during convocation. It is planned to repeat the training for those who were not able to attend. July 2017 - Training in regard to the Governmental Conduct Act will be held. As well, the HR Manager is developing a Code of Conduct specific to NNMC. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 -- The College President tasked the HR Director with drafting a Code of Conduct for all employees. During Convocation Week in August 2017, all employees will receive Government Conduct Act training, and will sign the Code of Conduct.
2016-015 | OPEN | NEW MEXICO PREHISTORIC AND HISTORIC SITES PRESERVATIONS ACTS VIOLATION |  | Noncompliance | State Law Compliance - Other | 2017-11-01 |  |  |  | August 2017 - Still in process. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-016 | CLOSED (awaiting validation by Internal Auditor) | INADEQUATE CONTROLS OVER SABBATICAL AND ANNUAL LEAVE |  | Material Weakness | Payroll and Related Liabilities | 2016-10-17 | 2016-10-17 |  |  | June 2017 -- The current College President's contract limits his activities so as not to interfere with the accomplishment of his NNMC duties. In addition, the Executive Assistant to the President has been diligent about overseeing and managing forms requesting time off for any activities not covered in the line of NNMC duties. An assessment of the President's calendar since Oct 17, 2016 (the current president's first day at NNMC) will confirm that all time off has been accounted for. May 2017 -- The current College President's contract limits his activities so as not to interfere with the accomplishment of his NNMC duties. In addition, the Executive Assistant to the President has been diligent about overseeing and managing forms requesting time off for any activities not covered in the line of NNMC duties. An assessment of the President's calendar since Oct 17, 2016 (the current president's first day at NNMC) will confirm that all time off has been accounted for.
2016-017 | OPEN | OUTDATED POLICIES AND PROCEDURES |  | Significant Deficiency | Lack of Policies, Procedures or Internal Control Stucture or Environment | 2018-11-01 |  |  |  | August 2017 - Work continues toward resolution. We are in the process of establishing a work group to attack this issue and hope to have the work group seated by the end of September 2017. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-018 | OPEN | LACK OF MONITORING AND CORRECTIVE ACTIONS |  | Material Weakness | Lack of Policies, Procedures, and Internal Control Structure or Environment | 2017-11-01 |  |  |  | August 2017 - As stated above, work continues toward evaluation and rewrite of internal controls. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 -- The College is beginning to draft a Request for Proposal (RFP) to hire an internal auditor on a contract basis. This individual will report directly to the Board of Regents and will update the BoR on the progress of audit finding improvements (and will serve as an independent validator for progress already achieved).
2016-019 | OPEN | LACK OF ESTABLISHED PRACTICES FOR THE IDENTIFICATION, MITIGATION AND MONITORING OF RISKS |  | Material Weakness | Lack of Policies, Procedures, and Internal Control Stucture or Environment | 2017-11-01 |  |  |  | August 2017 - As previously stated, internal controls for cash procedures have been established and documented. We will now procede to other areas potentially at risk. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 -- The College is beginning to draft a Request for Proposal (RFP) to hire an internal auditor on a contract basis. This individual will report directly to the Board of Regents and will update the BoR on the progress of audit finding improvements (and will serve as an independent validator for progress already achieved).
2016-020 | OPEN | BANK RECONCILIATIONS - STALE DATED CHECKS |  | Significant Deficiency | Cash and Investments | 2017-11-01 |  |  |  | August 2017 - Our IT Director has made great headway in automating the bank reconciliation process for NNMC. There was a snag with deposits that has been resolved by the use of numbered bank deposits. Once the numbered bank deposits are implemented, the process will be fully automated for all intents and purposes. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-021 | OPEN | REVIEW AND CLEAN-UP OF CLEARING AND SUSPENSE AND ACCOUNTS |  | Significant Deficiency | Revenue and Receivables | 2017-11-01 |  |  |  | August 2017 - review and clean is in the planning stage. A work group will have to be established. Some accounts receivable accounts have, by necessity, already been cleared; however, a written process must be established and drive toward total clean up is needed. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-022 | OPEN | PETTY CASH - SECURITY AND TRACKING |  | Material Weakness | Cash and Investments | 2017-11-01 |  |  |  | August 2017 - no progress made during the month of July. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-023 | OPEN | UNDERREPORTED PAYROLL TAX LIABILITIES |  | Significant Deficiency | Payroll and Related Liabilities | 2017-11-01 |  |  |  | August 2017 - Still in process. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-024 | OPEN | UNUSED CREDIT CARD MACHINES AND RELATED MONTHLY FEE |  | Significant Deficiency | Expenditures and Expenses - Other | 2017-07-01 |  |  |  | August 2017 - two machines have been returned and there is the possiblity that a credit of $492 was received. June 2017 - The College has begun the process of identifying machines that are not used and not needed. Those identified as not used and not needed will be elliminated (target date is the June 30, 2017). May 2017 -- The College President has asked the business office for inquiries about cancelling service with unused machines. Five of the nine credit card machines operated by the college are slated to be phased out, pending early cancellation penalties. The college expects this to be resolved quickly.
2016-025 | OPEN | RECONCILIATION OF STUDENT ACCOUNTS RECEIVABLE |  | Significant Deficiency | Revenues and Receivables | 2017-11-01 |  |  |  | August 2017 - As mentioned above, the position for Students Accounts Receivable has been hired from within the Business Office (Jessica Holguin). Jessica was handling accounts receivable on an interim basis and has now been appointed permanently. June 2017 - The College is in the process of hiring a Student Accounts Receivable person who will be responsible for ensuring that all aspects of the Student Accounts Receivable Process are appropriately established, documented and adhered to. This will be coordinated between the Accounting and Financial Aid Offices. May 2017 - In Progress
2016-026 | OPEN | ASSIGNED PERMISSIONS IN BANNER |  | Material Weakness | Information Technology | 2017-11-01 |  |  |  | August 2017 - The IT Director continues to make improvements in the process for assigning permissions throughout the entire IT network, including Banner. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-027 | OPEN | INFORMATION TECHNOLOGY (OTHER) |  | Material Weakness | Information Technology | 2017-11-01 |  |  |  | August 2017 - Still in process. May 2017 -- The College will be requesting the required electrical backup equipment at the NM Higher Education Department Capital Outlay Committee hearing scheduled for June 28, 2017. May 2017 -- The College will be requesting the required electrical backup equipment at the NM Higher Education Department Capital Outlay Committee hearing scheduled for June 28, 2017.
2016-028 | OPEN | TRACKING OF BANNER FEEDS TO ENSURE FEEDS ARE NOT SUSPENDED/DELETED |  | Significant Deficiency | Information Technology | 2017-11-01 |  |  |  | August 2017 - no change in status due to year-end activity and the beginning of the new fiscal year. June 2017 - A process is currently in devlopment that will track all suspended feeds. The College plans to implement the process by no later than July 1, 2017 May 2017 - In Progress
2016-029 | OPEN | COMPLIANCE VIOLATION - ANTI-DONATION CLAUSE OF THE NEW CONSTITUTION |  | Material Non-Compliance | State Law Compliance - Anti-Donation Clause | 2017-11-01 |  |  |  | August 2017 - During convocation week on Tuesday August 8, 2017, a discussion was held pertaining to the anti-donation clause to bring employee awareness to this critical issue. Employees were advised that all assets are State of NM assets and any change to location, usage, and/or disposal must be reviewed by executive management. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress
2016-030 | OPEN | RECONCILIATION OF STUDENT FINANCIAL AID DISBURSEMENTS |  | Material Weakness | Grants Compliance | 2017-11-01 |  |  |  | August 2017 - still in process. June 2017 - A review is currently under way to determine responsibility at the account level. The College is in the process of hiring a Student Accounts Receivable person. Accounting is coordinating with Financial Aid to utilize their knowledge and assistance. May 2017 - In Progress
2016-031 | OPEN | CONTROLS OVER RECORDING PAID TIME-OFF TO FEDERAL GRANTS |  | Significant Deficiency | Grant Compliance | 2017-11-01 |  |  |  | August 2017 - Work has begun in this area. The HR Director, Provost and VP for Fin & Admin are working toward resolution. June 2017 - The College is in the process of hiring a grants manager who will be responsible for ensure compliance at all levels of the grants process. May 2017 - In Progress
2016-032 | OPEN | LACK OF COMPLETE POLICIES AND PROCEDURES |  | Material Weakness and Non-Compliance | Grant Compliance | 2017-11-01 |  |  |  | Same as above, work continues toward resolution. June 2017 - A new Interim VP of Finance and Administration has been hired. The new VP is a CPA with a financial audit background and understanding of internal contgrols (including the COSO Framework). He is currently in the process of a complete assessment of the intenal control system. The initial focus will be on all cash activities. May 2017 - In Progress