## Sheet1
FINDING NUMBER | OPEN OR CLOSED | FINDING NAME | DESCRIPTION | TYPE OF FINDING | CATEGORY | TARGET COMPLETION DATE | DATE COMPLETED | COMPLETED BY | INTERNAL AUDITOR VALIDATION DATE | RECORD OF EFFORT | COMMENTS
2013-001 | OPEN | BANK RECONCILIATIONS | Timeliness and review process (repeated and updated) | Material Weakness | Cash & Investments | 2017-12-01 |  |  |  | February 2018 - No change from last month. December 2017 - The bank reconciliation process has been developed, implemented, and documented. Bank reconciliations for the College's operating account, the largest, are up to date as of December 2017. All smaller accounts are now in the process of completion so that they can be audited. November 2017 - There was a bit of a snag on the bank side of the reconciliation pertaining to deposits. Although we received numbered deposit slips, the slips did have an appropriate scan line so that they could be loaded into the system and read electroncially in order to match to the deposit numbers in Banner. This has been corrected and will be tested by November 21, 2017. Our contractor has made significant headway in documenting the cash reconciliation procedures utilizing the automated method. We believe we will be 100% complete with this corrective action by December 2017. Current Completion Percentage: 85%
2013-002 | OPEN | BANK RECONCILIATIONS | Timeliness and review process - Foundation (repeated and updated) | Material Weakness | Cash & Investments | 2017-12-01 |  |  |  | February 2018 - No change from last month. December 2017 - The bank reconciliation process has been developed, implemented, and documented. A contractor has been engaged in order to work toward completion of foundation bookkeeping, accounting and other tasks that include bank reconciliations. This will allow for audit of foundation accounts.
2013-003 | OPEN | CAPITAL ASSETS | Physical Inventory Certification & Safeguarding (repeated and updated) | Significant Deficiency | Capital Assets | 2018-06-01 |  |  |  | February 2018 - No change - December 2017 - No change for December 2017. November 2017 - Research continues on a number of items. Competion percentage: 94%
2013-007 | OPEN | DISASTER RECOVERY PLAN AND PASSWORD POLICIES | Repeated and updated | Significant Deficiency | Information Technology | 2017-08-11 |  |  |  | February 2018 - No Change over Last Month. December 2017 - No change over last month. January 2018 - No Change. November 2017 - No major change from previous month. Completion Percentage: 55%
2015-001 | OPEN | TRAVEL AND PER DIEM | Repeated and updates | Other Noncompliance | Travel and Per Diem |  |  |  |  | February 2018 - No change over previous month. December 2017 - No change over previous month. November 2017 - The Business Office Core Group has prioritzed the process of revising and re-implementing procedures for travel & per diem reimbursement requests. As well, the group has developed a new form for travel & reimbrusement requests that will be promulgated shortly. As well, training sessions will be held. Completion Percentage: 75%
2016-001 | OPEN | LATE AUDIT REPORT |  | Material Non-Compliance | Late Audits | 2017-11-01 |  |  |  | January 2018 - Report was due November 15, 2017; auditors were able to begin at the begin fieldwork in early January 2018. Targeted completion date is March 31, 2018. December 2017 - No ChangeNovember 2017 - No change from October. The audit contract was finalized 10/2/2017. The new auditor is REDW, LLC. The forensic review has not been completed. REDW, LLC will not begin the regular audit until the forensic team has completed its review and report. The audit will not be completed timely. The Office of the State Auditor has been informed. Completion Percentage: 0%
2016-002 | OPEN | POTENTIAL FRAUD, FORGERY, EMBEZZLEMENT, LARCENY AND NON-COMPLIANCE |  | Material Weakness | State Law Compliance - Other | 2017-11-01 |  |  |  | January 2018 - forensic reports are complete. We received the Recommendations Report on February 12, 2018. December 2017 - No change over last month. November 2017 - The forensic team was on-site November 6, 2017 to conduct additional interviews and fieldwork. The team was not able to conduct all the interviews required due to the fact that some of the interviews were more lengthy than expected and some staff called in sick or had planned leave. They will return November 29, 2017 to complete both interviews and wrap up field work by the 30th. The target date for the forensic report is currently set at December 15, 2017. Completion percentage: 85%
2016-003 | OPEN | INSUFFICIENT ATTENTION AND ACCOUNTABILITY OVER ACCOUNTING AND INTERNAL CONTROLS |  | Material Weakness | Financial Reporting | 2017-08-01 |  |  |  | January 2018 - with forensic accountants' recommendation, we can now move forward to implement recommendations and begin to mitigate this finding. December 2017 - No change over last month.November 2017 - We continue to work toward adequate documentation as well as revision of internal controls and procedures that assign responsibilities specifically to appropriate individuals. We also await the results of the forensic review in order to incorporate recommendations. Completion Percentage: 94%
2016-004 | OPEN | INSUFFICIENT SECURITY OF ACCOUNTING RECORDS/BACKUP OF ELECTRONIC DOCUMENTS |  | Material Weakness | State Law Compliance - Other | 2017-08-01 |  |  |  | January 2018 - with forensic accountants' recommendations, we can now move forward to implement recommdations in order to mitigate this finding. December 2017 - no change over previous month. November 2017 - No change from pervious month.
2016-005 | OPEN | PROCUREMENT CODE VIOLATIONS |  | Material Weakness | Procurement | 2017-11-01 |  |  |  | February 2017 - No change over previous month. November 2017 - To reiterate from September 2017, most of the approval process for procurement above $500 has been assumed by the VP for Finance & Admin due to lack of skill and training of current staff. RFPs and contracts are drafted and issued by the VP. Contracts are now also reviewed by new counsel Cuddy & McCarthy.
2016-006 | OPEN | SEGREGATION OF DUTIES |  | Material Weakness | Segregation of Duties | 2017-08-01 |  |  |  | January 2018 - duties will be further segregated in accordance with forensic accountants' recommendations. December 2017 - No change over previous month. November 2017 - Ongoing. Segregation of duties continue to be of paramount consideration as different types of situations arise. Completion Percentage: 70%
2016-007 | OPEN | FINANCIAL CLOSE AND REPORTING |  | Material Weakness | Financial Reporting | 2017-11-01 |  |  |  | February 2018 - no change from last month. December 2017 - No change over the previous month. November 2017 - Staff continues to work toward timely close out of months.
2016-008 | OPEN | LACK OF INTERNAL CONTROLS OVER CASH RECEPTS PROCESS |  | Material Weakness | Cash and Investments | 2017-11-01 |  |  |  | January 2018 - Completed in September 2017. December 2017 - No change over the previous month.November 2017 - 100% complete as of September 2017.
2016-009 | OPEN | LACK OF INTERNAL CONTROLS OVER CASH DISBURSEMENTS AND TRANSFER PROCESS |  | Material Weakness | Expenditures and Expenses - Other | 2017-11-01 |  |  |  | January 2018 - considered complete as of September 2017. December 2017 - No change over the previousl month. November 2017 - Considered 100% comlete as of September 2017. To reiterate, in addition to segregation of duties, VP for Finance & Administration reviews each and every disbursement at various levels of the process.
2016-010 | OPEN | LACK OF INTERNAL CONROLS OVER JOURNAL ENTRIES |  | Material Weakness | Lack of Policies, Procedures, and Internal Control Structure and Environment | 2017-11-01 |  |  |  | January 2018 - Considered complete as of September 2017.December 2017 - No change over the previous month. November 2017 - Considered 100% comlete as of September 2017. To reiterate, in addition to segregation of duties, VP for Finance & Administration reviews each and every journal entry for support and accuracy.
2016-011 | OPEN | NEW MEXICO STATE CONSTITUTION VIOLATION - BOARD MEMBER VACANCY |  | Non-Compliance | State Law Compliance - Other | Unknown |  |  |  | February 2018 - No Change over previous months.November 2017 - As of 10/13/2017 all regents have been appointed by the Governor of New Mexico, the Honorable Susana Martinez. 100% Complete
2016-012 | OPEN | TRANSFERS, DISPOSALS, AND TRACKING OF INVENTORY ITEMS LESS THAN $5,000 |  | Material Weakness | Inventory | 2017-11-01 |  |  |  | February 2018 - No Change. December 2017 - No change over the previous month. November 2017 - Same as Finding #2013-003. 94% complete. Research continues on a number of items. However, inventory is substantially updated and disposals will be made appropriately and accurately.
2016-013 | OPEN | PUBLIC MONEY ACTION VIOLATION - DEPOSITS NOT MADE WITHIN 24 HOURS |  | Non-Compliance | State Law Compliance - Public Money Act | 2017-11-01 |  |  |  | February 2018 - No change. December 2017 - No change over the previous month. November 2017 - Deposit process continues to be refined. New bank accounts have been established. Completion Percentage: 95%
2016-014 | OPEN | NON-COMPLIANCE WITH AND INADEQUATE CONTROLS OVER THE GOVERNMENTAL CONDUCT ACT |  | Non-Compliance | Lack of Policies, Procedures or Internal Controls | 2017-09-01 |  |  |  | February 2018 - No change. December 2017 - No change over the previous month. November 2017 - Same as October 2017. Approximately 95% complete.
2016-015 | OPEN | NEW MEXICO PREHISTORIC AND HISTORIC SITES PRESERVATIONS ACTS VIOLATION |  | Noncompliance | State Law Compliance - Other | 2017-11-01 |  |  |  | February 2018 - No change. December 2017 - No change over the previous month. November 2017 - No change. Nothing to report.
2016-016 | CLOSED (awaiting validation by Internal Auditor) | INADEQUATE CONTROLS OVER SABBATICAL AND ANNUAL LEAVE |  | Material Weakness | Payroll and Related Liabilities | 2016-10-17 | 2016-10-17 |  |  | February 2018 - No change.December 2017 - No change over the previous month. November 2017 - Considered 100% complete as of September 2017.
2016-017 | OPEN | OUTDATED POLICIES AND PROCEDURES |  | Significant Deficiency | Lack of Policies, Procedures or Internal Control Structure or Environment | 2018-11-01 |  |  |  | February 2018 - No change. December 2017 - Documentation continues; no significant changes over the previous month.November 2017 - A contractor has been hired to assist in audit preparation. When the contractor has completed audit prep tasks, he will begin documentation of internal control.
2016-018 | OPEN | LACK OF MONITORING AND CORRECTIVE ACTIONS |  | Material Weakness | Lack of Policies, Procedures, and Internal Control Structure or Environment | 2017-11-01 |  |  |  | February 2018 - No change. December 2017 - No change over the previous month. November 2017 - Same as Finding above.
2016-019 | OPEN | LACK OF ESTABLISHED PRACTICES FOR THE IDENTIFICATION, MITIGATION AND MONITORING OF RISKS |  | Material Weakness | Lack of Policies, Procedures, and Internal Control Structure or Environment | 2017-11-01 |  |  |  | February 2018 - No change. December 2017 - No change over the previous month. November 2017 - Same as Finding above.
2016-020 | OPEN | BANK RECONCILIATIONS - STALE DATED CHECKS |  | Significant Deficiency | Cash and Investments | 2017-11-01 |  |  |  | February 2018 - No change. December 2017 - No change over the previous month. November 2017 - Same as progress for Finding 2013-001. Approximately 85% complete.
2016-021 | OPEN | REVIEW AND CLEAN-UP OF CLEARING AND SUSPENSE AND ACCOUNTS |  | Significant Deficiency | Revenue and Receivables | 2017-11-01 |  |  |  | February 2018 - No change. December 2017 - No change over the previous month. November 2017 - Ongoing. Work continues. Finding resolution is approximately 80% complete.
2016-022 | OPEN | PETTY CASH - SECURITY AND TRACKING |  | Material Weakness | Cash and Investments | 2017-11-01 |  |  |  | February 2018 - no change. December 2017 - No change over the previous month.November 2017 - No change. Nothing to report.
2016-023 | OPEN | UNDERREPORTED PAYROLL TAX LIABILITIES |  | Significant Deficiency | Payroll and Related Liabilities | 2017-11-01 |  |  |  | February 2018 - No Change. December 2017 - No change over the previous month.November 2017 - College considers this 100% complete with regard to the current period.
2016-024 | OPEN | UNUSED CREDIT CARD MACHINES AND RELATED MONTHLY FEE |  | Significant Deficiency | Expenditures and Expenses - Other | 2017-07-01 |  |  |  | February 2018 - no change; completed in previous months. December 2017 - No change over the previous month.November 2017 - Considered 100% complete as of September 2017.
2016-025 | OPEN | RECONCILIATION OF STUDENT ACCOUNTS RECEIVABLE |  | Significant Deficiency | Revenues and Receivables | 2017-11-01 |  |  |  | January 2018 - completed in previous months. December 2017 - No change over the previous month.November 2017 - Considered 100% complete as of September 2017.
2016-026 | OPEN | ASSIGNED PERMISSIONS IN BANNER |  | Material Weakness | Information Technology | 2017-11-01 |  |  |  | February 2018 - no change. December 2017 - No change over the previous month.November 2017 - No change. Nothing to report.
2016-027 | OPEN | INFORMATION TECHNOLOGY (OTHER) |  | Material Weakness | Information Technology | 2017-11-01 |  |  |  | February 2018 - no change. December 2017 - No change over the previous month.November 2017 - Same as September 2017. Approximately 50% complete.
2016-028 | OPEN | TRACKING OF BANNER FEEDS TO ENSURE FEEDS ARE NOT SUSPENDED/DELETED |  | Significant Deficiency | Information Technology | 2017-11-01 |  |  |  | January 2018 - completed in previous months. December 2017 - No change over the previous month.November 2017 - 100% complete.
2016-029 | OPEN | COMPLIANCE VIOLATION - ANTI-DONATION CLAUSE OF THE NEW CONSTITUTION |  | Material Non-Compliance | State Law Compliance - Anti-Donation Clause | 2017-11-01 |  |  |  | Janaury 2018 - compleged in previous months. December 2017 - No change over the previous month.November 2017 - 100% complete as of August 2017.
2016-030 | OPEN | RECONCILIATION OF STUDENT FINANCIAL AID DISBURSEMENTS |  | Material Weakness | Grants Compliance | 2017-11-01 |  |  |  | February 2018 - No change.December 2017 - No change over the previous month.November 2017 - Same as Finding for 2016-025. 100% complete.
2016-031 | OPEN | CONTROLS OVER RECORDING PAID TIME-OFF TO FEDERAL GRANTS |  | Significant Deficiency | Grant Compliance | 2017-11-01 |  |  |  | February 2018 - no change. December 2017 - No change over the previous month.November 2017 - 100% complete.
2016-032 | OPEN | LACK OF COMPLETE POLICIES AND PROCEDURES |  | Material Weakness and Non-Compliance | Grant Compliance | 2017-11-01 |  |  |  | February 2018 - No change. December 2017 - No change over the previous month.November 2017 - A CGFM has been hired through contract. The contractor has begin work on documentation of policies and procedures as soon as other urgent work is completed. The contractor has focused on policies and procedures for the automated bank reconciliation process as a priority.